## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a new user, I want to create an account so that I can access the system and use its features. | Given I am a new user, when I try to make an account with an unused username, the system registers my profile and creates an account. | Pass | HS; 7/7 | Pass | HS; 7/27;
| Given I am a new user, when I try to make an account with a taken username, the system refuses the attempt and offers to redirect to login. | Pass | HS; 7/7 create and login are not seperate pages so there technically isnt a redirect, but the current arrangement of seperate buttons on the same page works fine | Pass | HS; 7/27;
| Given I already have an account, when I accept the system’s offer to redirect to login, the system sends me to the login. | Pass | HS; 7/7; again, technically no redirect, but works fine | Pass | HS; 7/27;
| Given I do not already have an account, when I refuse the system’s offer to redirect to login, the system lets me try to make a new account with a different username. | Pass | HS; 7/7; again, technically no redirect, but works fine | Pass | HS; 7/27;
| Given the username is “admin”, when I make an account with that username, it has all the permissions and functionality of a manager account. | Pass | HS; 7/7; manager should not have access to basket UPDATE: manager's access to basket removed, now passes | Pass | HS; 7/27;
| Given any other username, when I make an account with that username, it has all the permissions and functionality of a helper account. | Pass | HS; 7/7; helper should not have access to Add need UPDATE: Helper's acces to Add needs removed; Now passes | Pass | HS; 7/27;
| Given my intended username does not meet system username requirements, when I try to make an account, the system refuses the attempt, provides feedback, and lets me retry. | Pass | HS; 7/7; feedback does not indicate what username requirements are and is therefore not helpful UPDATE: login page now shows username requirements; now passes | Pass | HS; 7/27;
As a registered user, I want to log in to my account so that I can access my saved information and functionality. | Given I already have an account, when I put in my correct username and correct password, the system logs me into my account. | Pass | HS; 7/7; again, technically no redirect, but works fine | Pass | HS; 7/27;
| Given I already have an account, when I put in my correct username and an incorrect password, the system denies me entry and lets me retry. | Pass | HS; 7/7; again, technically no redirect, but works fine | Pass | HS; 7/27;
| Given the username is not in the system, when I try to log in, the system warns me and offers to redirect to creating an account. | Pass | HS; 7/7; again, technically no redirect, but works fine | Pass | HS; 7/27;
| Given I am a new user without an account, when I accept the redirect offer, I am successfully redirected to create a new account. | Pass | HS; 7/7; again, technically no redirect, but works fine | Pass | HS; 7/27;
| Given I am a user with an account, when I decline the redirect offer, I am able to try logging in again. | Pass | HS; 7/7; again, technically no redirect, but works fine | Pass | HS; 7/27;
As a logged-in user, I want to log out of my account so that my session is ended securely. | Given I am not logged into any account, when I'm on the Angular website, then the Log Out button is not visible. | Pass | HS; 7/7 | Pass | HS; 7/27;
| Given I am logged into any account, when I click the Log Out component, then the Log Out event is triggered and the account is no longer logged in. | Pass | HS; 7/7 | Pass | HS; 7/27;
As a helper or manager, I want to view the cupboard and its needs so that I can browse available needs. | Given I am logged into a helper or manager account, when I am on the cupboard page, I can see the full list of needs that the cupboard contains. | Pass | HS; 7/7; | Pass | HS; 7/27;
| Given I am logged into a helper or manager account, when I select a specific need, I can expand/view the need’s details. | Pass | HS; 7/7; | Pass | HS; 7/27;
| Given I am logged into a helper account, when I am on the cupboard page, I have access to helper-specific controls. | Pass | HS; 7/7; only sees add to basket, which is correct, does not see buttons to manipulate needs | Pass | HS; 7/27;
| Given I am logged into a manager account, when I am on the cupboard page, I have access to manager-specific controls. | Pass | HS; 7/7; only sees add, edit, & delete need , which is correct. does not see add to basket | Pass | HS; 7/27;
As a helper or manager, I want to search and filter needs in the cupboard so that I can find relevant needs more easily. | Given I am logged into a helper or manager account, when I search the cupboard with an empty search string but checked types, the search returns matching needs. | Fail | HS; 7/7; no checked types functionality | Pass | HS; 7/27;
| Given I am logged into a helper or manager account, when I search the cupboard with an empty search string and no selected types, the search returns the full cupboard. | Fail | HS; 7/7; no checked types functionality | Pass | HS; 7/27;
As a helper, I want to add a need to my funding basket so that I can contribute to it later. | Given I am logged into a helper account, when I select a need, I can send it to the funding basket. | Pass | HS; 7/7; not technically selecting, but option is still presented and works | Pass | HS; 7/27;
| Given I am logged into a helper account, when I send a need to the funding basket, it shows up in the funding basket. | Pass | HS; 7/7; | Pass | HS; 7/27;
| Given the need is already in the funding basket, when I try to send it there, the system tells me that it’s already in there and refuses to duplicate it. | Pass | HS; 7/7; | Pass | HS; 7/27;
As a helper, I want to remove a need from my funding basket so that I can change my contribution choices. | Given I am logged into a helper account, when I select a need, I can remove it from the funding basket. | Pass | HS; 7/7; not technically selecting, but option is still presented and works | Pass | HS; 7/27;
| Given I am logged into a helper account, when I remove a need from the funding basket, it no longer shows up there. | Pass | HS; 7/7; | Pass | HS; 7/27;
As a helper, I want to view my funding basket so that I can review the needs I have selected. | Given I am logged into a helper account, when I access the funding basket, the system shows me the correct contents. | Pass | HS; 7/7; | Pass | HS; 7/27;
As a helper, I want to proceed to checkout from my funding basket so that I can complete my contribution. | Given I have nothing in the funding basket, when I try to check out, the system refuses the request. | Pass | HS; 7/7; handled entirely on frontend | Pass | HS; 7/27;
| Given I have something in the funding basket, when I try to check out, the system proceeds to checkout. | Pass | HS; 7/7; handled entirely on frontend | Pass | HS; 7/27;
As a helper, I want to complete the checkout process so that my contribution is successfully submitted. | Given I am checking out and have filled out the necessary fields, when I try to complete checkout, the system accepts the funds, removes the needs, and gives a confirmation. | Pass | JS; 7/7 | Pass | HS; 7/27;
| Given I am checking out and the necessary fields are incomplete, when I try to check out, the system tells me to complete them. | Pass | HS; 7/7; handled entirely on frontend | Pass | HS; 7/27;
As a helper, I want to cancel the checkout process so that I can return to my funding basket without completing the transaction. | Given I am in checkout, when I try to cancel checkout, the system asks me to confirm. | Pass | HS; 7/7; handled entirely on frontend | Pass | HS; 7/27;
| Given I am canceling checkout, when I confirm, the system returns me to the funding basket. | Pass | HS; 7/7; handled entirely on frontend | Pass | HS; 7/27;
| Given I cancel the cancellation, the system lets me continue checkout. | Pass | HS; 7/7; handled entirely on frontend | Pass | HS; 7/27;
As a manager, I want to add needs to the cupboard so that helpers can contribute to them. | Given I am logged into my manager account, when I try to add a need that does not already exist, the system updates the cupboard. | Pass | HS; 7/7; | Pass | HS; 7/27;
| Given I am logged into my manager account, when I try to add a need that already exists, the system refuses the request. | Pass | HS; 7/7; (already exists is defined as same name) | Pass | HS; 7/27;
| Given the need’s required fields are not complete, when I try to add the need, the system warns me and lets me complete them. | Pass | HS; 7/7; all fields are required | Pass | HS; 7/27;
As a manager, I want to remove needs from the cupboard so that outdated or unnecessary needs are no longer available. | Given I am logged into my manager account, when I try to remove a selected need, the system asks me to confirm. | Pass | HS; 7/7 | Pass | HS; 7/27;
| Given I confirm removal, the system updates the contents of the cupboard. | Pass | HS; 7/7 | Pass | HS; 7/27;
| Given I cancel removal, the system returns me to the unchanged cupboard. | Pass | HS; 7/7 | Pass | HS; 7/27;
As a manager, I want to edit a need's details so that the information remains accurate and up to date. | Given I am logged into my manager account, when I open a need’s edit interface, I can change its details. | Pass | HS; 7/7 | Pass | HS; 7/27;
| Given I have unsaved changes, when I try to leave, the system asks me to save or discard them. | Pass | HS; 7/7; does not ask to save when logging out, closing window, using navbar (Update: Feature has been created and confirmed to work by JS) | Pass | HS; 7/27;
| Given I select save, the cupboard is updated. | Pass | HS; 7/7 | Pass | HS; 7/27;
| Given I select cancel, the need remains unchanged. | Pass | HS; 7/7 | Pass | HS; 7/27;
As a helper, I want my funding basket to be saved when I leave or log out so that I do not lose my selections. | Given I am logged in as a Helper, when I exit the Angular website with a populated funding basket, that funding basket's contents are saved. | Pass | HS; 7/7; basket is not saved in account information, there is a singlular shared basked that shows up for everything UPDATE: Basket is saved on exit, now passes | Pass | HS; 7/27;
| Given I am logged in as a Helper, when I log out with a populated funding basket, the funding basket's contents are saved. | Pass | HS; 7/7; basket is not saved in account information, there is a singlular shared basked that shows up for everything UPDATE: Basket is saved on log out, now passes | Pass | HS; 7/27;
As a helper, I want my saved funding basket loaded when I log in so that I can continue where I left off. | Given I have a helper account with a saved funding basket, when I log in, the system loads the contents of my funding basket. | Pass | HS; 7/7; basket is not saved in account information, there is a singlular shared basked that shows up for everything UPDATE: each helper has a seperate basket that loads, now passes | Pass | HS; 7/27;
As a user, I want to view all organizations in the system so I know which ones are present. | Given I have a valid account, when I am logged in, I can see a link to the organizations view in the navbar |  |  | Pass | HS; 7/27;
| Given I am logged in to my account, when I navigate to the organizations view, I can see a readable list of current organizations. |  |  | Pass | HS; 7/27;
| Given I am logged into a helper account, when I view the organizations view, I am given access to only the helper specific controls |  |  | Pass | HS; 7/27;
| Given I am logged into a manager account, when I view the organizations view, I am given access to only the manager specific controls |  |  | Pass | HS; 7/27;
As a user, I want to view an organization’s details so I can know more about it | Given I am viewing the organizations, when I select an organization, I can see its details. |  |  | Pass | HS; 7/27;
| Given I am viewing an organization’s details, when I click back, the system returns me to the organization list. |  |  | Pass | HS; 7/27;
As a manager, I want to edit an organization so I can update its information if it changes. | Given I am logged into a manager account, when I view an organization in the list/org detail, then I see the text field to edit it |  |  | Pass | HS; 7/27;
| Given I am logged into a manager account, when I click the edit button, then the edits are saved. |  |  | Pass | HS; 7/27;
| Given I am editing the org, when I submit the edit, then the org is edited in the system |  |  | Pass | HS; 7/27;
| Given I am editing the org, when I submit the edit, then the needs with the organization are updated |  |  | Fail | HS; 7/27; need does not update after org does. tends to also break some other needs and orgs related functions that are performed after it
As a manager, I want to create an organization so it can be affiliated with needs in the system. | Given I am logged into my manager account, when I view the list of organizations, I see a button to add an organization. |  |  | Pass | HS; 7/27;
| Given I am logged into my manager account, when I go to create an organization, the system shows me the form to do so. |  |  | Pass | HS; 7/27;
| Given the form has some required fields blank, when I click create, the system refuses the request and warns me of the missing data. |  |  | Pass | HS; 7/27;
| Given the form has all the required information and is not present in the system, when I click create, the organization is added to the system and I am routed to the organization's view. |  |  | Pass | HS; 7/27;
| Given the form has all the required information but is already present in the system, when I click create, the system informs me and refuses the request. |  |  | Pass | HS; 7/27;
| Given I am creating an organization, when I click the cancel button, the system asks me to confirm the cancellation. |  |  | Pass | HS; 7/27;
| Given I want to cancel creating an organization, when I click confirm, the system reroutes me to the organizations view and does not create an organization |  |  | Pass | HS; 7/27;
| Given I do not want to cancel creating an organization, when I click cancel on the cancel confirmation view, the system lets me continue creating an organization |  |  | Pass | HS; 7/27;
| Given I have created an organization, when I look at the list of organizations, then new organization is shown in its contents. |  |  | Pass | HS; 7/27;
As a manager, I want to delete an organization so their affiliations can be removed from the system. | Given I am logged into my manager account, when I view an organization in the list and/or org detail view, I see a button to delete it. |  |  | Pass | HS; 7/27;
| Given I am logged into my manager account, when I click the delete button, i am asked to confirm org deletion. |  |  | Pass | HS; 7/27;
| Given I am deleting the org, when I click confirm, the org is removed from the system. |  |  | Pass | HS; 7/27;
| Given I am deleting the org, when I click confirm, all needs affiliated with that org are deleted. |  |  | Pass | HS; 7/27;
| Given I am not deleting the org, when I click cancel, the org remains in the system. |  |  | Pass | HS; 7/27;
As a user, I want to be able to view proposals created by all helpers so I can see what proposals have been made. | Given I am logged into my account, I can see a link to the proposals list in the navbar |  |  | Pass | HS; 7/27;
| Given I am logged into my account, when I navigate to the proposals list, I can see the readable list of proposals that have been made |  |  | Pass | HS; 7/27;
| Given I am logged into a helper account, when I view the proposal view, I am given access to only the helper specific controls |  |  | Pass | HS; 7/27;
| Given I am logged into a manager account, when I view the proposal view, I am given access to only the manager specific controls |  |  | Pass | HS; 7/27;
As a user, I want to view the details of a proposal so I can know more about it. | Given I am viewing the proposal, when I select a proposal, I can see its details. |  |  | Pass | HS; 7/27;
| Given I am viewing a proposal’s details, when I click back, the system returns me to the proposal list. |  |  | Pass | HS; 7/27;
As a helper, I want to see the status of a proposal so I can know if it is unreviewed, approved, or rejected. | Given I am logged in to my account, when I am viewing the proposal list, I see a visual indicator of its status. |  |  | Pass | HS; 7/27;
| Given I am logged into my account, when I am viewing a proposal’s details, I see a visual indicator of its status. |  |  | Pass | HS; 7/27;
As a user, I want to see votes for and against a proposal to help determine its suitability for the system. | Given I am logged in to my manager account, when I view a proposal, I can see the number of votes for and against the proposal. |  |  | Pass | HS; 7/27;
As a manager, I want to add or remove an organization to a need so that I can record their affiliation with that need | Given I am logged in as a manger, when I try to create a need, then the organization field appears in the form |  |  | Pass | HS; 7/27;
| Given I have added an organization, when I click the update need button, then the organization is updated and associated with that need |  |  | Pass | HS; 7/27;
| Given I have selected the 'No Org' option, when I click the update need button, then the need is affiliated with no organization |  |  | Fail | HS; 7/27; vestigial acceptance criteria from before we changed how our orgs and needs would interact
| Given I do not want to add orgs, when I click cancel, then the need is unchanged |  |  | Fail | HS; 7/27; vestigial acceptance criteria from before we changed how our orgs and needs would interact
| Given I am using the Edit Need page, when I view the edit need's options, then I get an option to edit the organization of the need. |  |  | Pass | HS; 7/27;
As a user, I want to sort/filter cupboards by organization so I can view needs by their affiliation. | Given I am logged in as a user, when I view the cupboard, then I can also view the list of available organizations. |  |  | Pass | HS; 7/27;
| Given I am logged in as a user, when I select any organizations in the cupboard's list, then I only get search results of needs affiliated with the selected organization. |  |  | Pass | HS; 7/27;
| Given I am logged in as a user, when I do not select any organization in the cupboard's list, then the search for needs doesn't restrict itself to any organizations |  |  | Pass | HS; 7/27;
As a helper, I want to know what needs are affiliated with each organization so that I can contribute to the desired organizations | Given I am logged in as a user, when I view a need's details, then the need's organization should be visible |  |  | Pass | HS; 7/27;
| Given I am logged in as a user, when I view a need in the cupboard, then the need's organization should be visible with the corresponding need |  |  | Pass | HS; 7/27;
| Given I am logged in as a user, when I click on the organization of the need, then I am taken to the details page of that organization |  |  | Pass | HS; 7/27;
As a helper, I want to create need proposals so that they can be reviewed for addition to the system. | Given I am logged in to my helper account, when I click the create proposal button, the system shows me the form to create a new one. |  |  | Pass | HS; 7/27;
| Given the form has some required fields blank, when I click create, the system refuses the request and warns me of the missing data. |  |  | Pass | HS; 7/27;
| Given the form has all the required information and is not present in the system, when I click create, the proposal is added to the system and I am routed to the proposal list view. |  |  | Pass | HS; 7/27;
| Given the form has all the required information but is already present in the system, when I click create, the system informs me and refuses the request. |  |  | Pass | HS; 7/27;
| Given I am creating a proposal, when I click the cancel button, the system asks me to confirm the cancellation. |  |  | Pass | HS; 7/27;
| Given I want to cancel creating a proposal, when I click confirm, the system reroutes me to the proposal list view and does not create a proposal |  |  | Pass | HS; 7/27;
| Given I do not want to cancel creating a proposal, when I click cancel on the cancel confirmation view, the system lets me continue creating a proposal |  |  | Pass | HS; 7/27;
| Given I have created a proposal, when I look at the list of proposals, the new proposal is shown in its contents. |  |  | Pass | HS; 7/27;
As a Helper, I want to be able to vote on a proposal so I can show my approval of the proposed need. | Given I am logged in to my helper account, when I view a proposal, there is a visual indication that I can vote for or against it. |  |  | Pass | HS; 7/27;
| Given I am logged in to my helper account, when I click vote for or vote against, the proposal's vote count updates by 1 in that direction. |  |  | Pass | HS; 7/27;
| Given I have already cast a vote in one direction, when I click that same direction again, my vote is removed. When I click the opposite direction instead, my vote switches to that direction. |  |  | Pass | HS; 7/27;
As a user, I want to search the proposals so I can view only the ones that meet certain criteria | Given I am logged into my account, when I view the proposals, I can see a search bar. |  |  | Pass | HS; 7/27;
| Given I type in a string to search bar, when I click the search button, the system only displays proposals include that name. |  |  | Pass | HS; 7/27;
| Given the string is empty, when I click the search button, the system shows all proposals. |  |  | Pass | HS; 7/27;
As a manager, I want to approve proposals that are suitable for the system so they can be added as needs. | Given I am logged in to a manager account, when I view a proposal, I have the option to approve it. |  |  | Pass | HS; 7/27;
| Given I am logged in to my manager account, when I accept a proposal, the system updates the status of the proposal to accepted. |  |  | Pass | HS; 7/27;
| Given I am logged in to my manager account, when I accept a proposal, the system converts it to a Need |  |  | Pass | HS; 7/27;
As a manager, I want to reject proposals that are not suitable for the system so I can prevent them from being added as a need. | Given I am logged in to a manager account, when I view a proposal, I have the option to reject it. |  |  | Pass | HS; 7/27;
| Given I am logged in to my manager account, when I reject a proposal, the system updates the status of the proposal to rejected. |  |  | Pass | HS; 7/27;
| Given I am logged in to my manager account, when I reject a proposal, Needs remain unchanged. |  |  | Pass | HS; 7/27;